## Slide 1: Lightning standup 1
Team 2

## Slide 2: Progress
Building a “gold-standard”
  Started running two approaches (mmseqs2 and synteny based approach) to identify all contig contaminants within one of the marine metagenomes (compared to other samples)
  Agreed on blast tabulated output format
  Both the query and reference represent longer contigs (> 500 base-pairs)
Implementing Benchmarking Framework
  Minimal Snakemake workflow is running from start to finish
  Execute the workflow on AWS EC2 instance
  Generate a metrics report
Implementing Solutions
  Exploring ordered Minhash sketch based approach
  Comparing to MashScreen/Dashing etc.
Problem: Given a query contig c, and a database of sequences(contigs from multiple assemblies) return a set of contigs that either contain the query contig c or contained in the query. A contig q is contained in contig s if the ANI between q and c is at least 95% and it covers more than 95% of the length of the shortest contig

## Slide 3: Road blocks
Defining a “gold-standard” -- what existing methods will give us the “correct”/“true” output to evaluate against